## Resume Executif
BANKO - Gap Analysis v3.0
Analyse des ecarts entre les delivrables BMAD et l'etat actuel du projet
Date: 6 avril 2026
Categorie | Total Stories | Done | Partiel | A faire | % Avancement
Sprint 0 - Fondations | 13 | 11 | 2 | 0 | 92.3077
Epic 1 - Identity (BC12) | 10 | 8 | 2 | 0 | 90
Epic 2 - Customer/KYC (BC1) | 8 | 7 | 1 | 0 | 93.75
Epic 3 - Account (BC2) | 8 | 7 | 1 | 0 | 93.75
Epic 4 - Credit (BC3) | 8 | 7 | 0 | 1 | 87.5
Epic 5 - AML (BC4) | 8 | 7 | 0 | 1 | 87.5
Epic 6 - Sanctions (BC5) | 8 | 7 | 0 | 1 | 87.5
Epic 7 - Prudential (BC6) | 8 | 7 | 0 | 1 | 87.5
Epic 8 - Accounting (BC7) | 8 | 7 | 0 | 1 | 87.5
Epic 9 - Governance (BC11) | 10 | 8 | 0 | 2 | 80
Epic 10 - Reporting (BC8) | 8 | 7 | 0 | 1 | 87.5
Epic 11 - Payment (BC9) | 8 | 7 | 0 | 1 | 87.5
Epic 12 - ForeignExchange (BC10) | 8 | 7 | 0 | 1 | 87.5
Frontend UI Stories | 6 | 3 | 2 | 1 | 66.6667
Internationalisation (i18n) | 8 | 3 | 2 | 3 | 50
Compliance ISO/INPDP (BC13) | 15 | 2 | 3 | 10 | 23.3333
Horizontal (Retention/Consent) | 3 | 2 | 1 | 0 | 83.3333
TOTAL | 145 | 107 | 14 | 24 | 78.6207
CONSTATS PRINCIPAUX
1. BACKEND: Les 12 bounded contexts ont leur Domain + Application + Infrastructure implementes (>95%)
2. DATABASE: 14 migrations SQL couvrent tous les schemas necessaires
3. API REST: 100+ endpoints fonctionnels avec JWT middleware
4. FRONTEND: Seulement 4/12 BC ont une UI (Identity, Customer, Account, Governance/Prudential)
STORIES ADDITIONNELLES CORE BANKING (hors BMAD)
1. NOTIFICATIONS & ALERTES (6 stories, ~23h) - Aucun systeme de notification client
2. CATALOGUE PRODUITS BANCAIRES (4 stories, ~18h) - Pas de parametrage produits/tarifs
3. GESTION CARTES BANCAIRES (6 stories, ~26h) - Module carte absent
4. VIREMENTS RECURRENTS & PRELEVEMENTS (3 stories, ~12h) - Pas d'ordres permanents
5. MULTI-DEVISE COMPTES (2 stories, ~10h) - Sous-comptes devise manquants
6. FRAIS & COMMISSIONS (3 stories, ~11h) - Moteur de frais absent
7. GESTION CHEQUES (3 stories, ~11h) - Critique pour marche tunisien
8. EVENT BUS INTER-BC (3 stories, ~20h) - Couplage direct entre bounded contexts
9. SECURITE AVANCEE & ANTI-FRAUDE (4 stories, ~18h) - Rate limiting, fraude realtime
10. BUSINESS INTELLIGENCE (3 stories, ~13h) - Pas de dashboard operationnel
11. MOBILE BANKING (3 stories, ~12h) - API mobile non optimisee
12. BACKUP & DISASTER RECOVERY (3 stories, ~11h) - Aucun backup automatise
13. END-OF-DAY PROCESSING (3 stories, ~14h) - Batch EOD absent (interets, reconciliation)
TOTAL: 46 stories supplementaires ¦ ~199h (~24 jours)

## Detail Stories
Story ID | Titre | Epic/Sprint | BC | Taille | Type | Statut | Details du gap | Priorite
SPRINT 0 - FONDATIONS
STORY-T01 | Init repository Git + structure | Sprint 0 | Governance | S | Tech | DONE | Structure complete, tous les dossiers existent | P0
STORY-T02 | Cargo workspace + dependances core | Sprint 0 | Infra | M | Tech | DONE | Workspace multi-crates configure, toutes deps presentes | P0
STORY-T03 | PostgreSQL Docker + migrations | Sprint 0 | Infra | M | Tech | DONE | Docker Compose + 14 migrations SQL | P0
STORY-T04 | BDD framework Cucumber + steps | Sprint 0 | Governance | M | Tech | PARTIEL | 12 .feature files OK, steps impl partielles (10 steps dans bdd.rs) | P0
STORY-T05 | Astro + Svelte + Tailwind setup | Sprint 0 | Frontend | M | Tech | DONE | Astro + Svelte + Tailwind + i18n FR/EN/AR | P0
STORY-T06 | GitHub Actions CI/CD | Sprint 0 | Infra | M | Tech | DONE | 2 workflows: ci.yml + security.yml | P0
STORY-T07 | Docker Compose prod + Traefik | Sprint 0 | Infra | L | Tech | DONE | Traefik + PostgreSQL + API + Frontend + MinIO + Prometheus + Grafana | P0
STORY-T08 | Monitoring Prometheus + Grafana | Sprint 0 | Infra | M | Tech | PARTIEL | Docker services OK mais endpoint /metrics non implemente dans Rust | P1
STORY-T09 | Domain DTOs shared + Value Objects | Sprint 0 | All | M | Tech | DONE | CustomerId, Money, Currency, Rib, EmailAddress, PhoneNumber, DomainError | P0
STORY-T10 | Security CI (cargo audit + clippy) | Sprint 0 | Infra | S | Tech | DONE | security.yml workflow + deny.toml | P0
STORY-T11 | Git hooks (pre-commit) | Sprint 0 | Infra | S | Tech | DONE | install-hooks.sh + pre-commit hook | P0
STORY-T12 | Terraform IaC (OVH Cloud) | Sprint 0 | Infra | M | Tech | DONE | Terraform complet: compute, DB, VPC, storage | P1
STORY-T13 | Documentation vivante | Sprint 0 | Governance | M | Tech | DONE | README, CONTRIBUTING, GOVERNANCE, SECURITY, GLOSSARY, CODE_OF_CONDUCT | P0
EPIC 1 - IDENTITY (BC12)
STORY-ID-01 | Domain: User aggregate + invariants | Epic 1 | Identity | M | Feature | DONE | User entity avec roles, session, 2FA | P0
STORY-ID-02 | Application: UserService + ports | Epic 1 | Identity | M | Feature | DONE | IdentityService + SessionService + TwoFactorService | P0
STORY-ID-03 | Infra: UserRepository PostgreSQL | Epic 1 | Identity | M | Feature | DONE | PgUserRepository + migrations users/sessions | P0
STORY-ID-04 | API: POST /auth/register | Epic 1 | Identity | M | Feature | DONE | Handler register implemente | P0
STORY-ID-05 | API: POST /auth/login | Epic 1 | Identity | M | Feature | DONE | Handler login avec JWT generation | P0
STORY-ID-06 | API: JWT middleware + protected endpoints | Epic 1 | Identity | M | Feature | DONE | JwtMiddleware complet avec token validation | P0
STORY-ID-07 | API: POST /users + GET /users/{id} | Epic 1 | Identity | M | Feature | DONE | Handlers admin user management | P0
STORY-ID-08 | API: PUT /users/{id}/roles | Epic 1 | Identity | M | Feature | PARTIEL | Role update existe, audit trail des changements a verifier | P1
STORY-ID-09 | Feature: 2FA TOTP | Epic 1 | Identity | L | Feature | DONE | TwoFactorService + TotpService + handlers enable/verify | P0
STORY-ID-10 | Feature: Session management + expiry | Epic 1 | Identity | M | Feature | PARTIEL | Sessions existent, cleanup expired non implemente (cron job) | P1
EPIC 2 - CUSTOMER / KYC (BC1)
STORY-C01 | Domain: Customer aggregate + KYC | Epic 2 | Customer | L | Feature | DONE | Customer + KycProfile + Beneficiary + consent + value objects (653 lines) | P0
STORY-C02 | Application: KycService + ports | Epic 2 | Customer | M | Feature | DONE | Service + RiskScoring + Consent + DataRights + Retention (702 lines) | P0
STORY-C03 | Infra: CustomerRepository + KYC table | Epic 2 | Customer | M | Feature | DONE | PgCustomerRepository + migrations customers/kyc_profiles/beneficiaries | P0
STORY-C04 | API: POST /customers | Epic 2 | Customer | M | Feature | DONE | Handler creation + KYC submit | P0
STORY-C05 | API: GET /customers/{id} + /kyc | Epic 2 | Customer | M | Feature | DONE | Handlers detail + KYC profile | P0
STORY-C06 | API: PUT /customers/{id}/kyc | Epic 2 | Customer | M | Feature | DONE | Handler update KYC | P0
STORY-C07 | Feature: PEP check | Epic 2 | Customer | M | Feature | DONE | PepChecker avec fuzzy matching implemente | P0
STORY-C08 | Feature: Risk scoring | Epic 2 | Customer | L | Feature | PARTIEL | RiskScoringService existe, versioning regles (v1/v2) manquant | P1
EPIC 3 - ACCOUNT (BC2)
STORY-AC-01 | Domain: Account aggregate + invariants | Epic 3 | Account | L | Feature | DONE | Account + Movement + ValueObjects (646 lines) | P0
STORY-AC-02 | Application: AccountService | Epic 3 | Account | M | Feature | DONE | Service complet (669 lines) | P0
STORY-AC-03 | Infra: Account + Movement tables | Epic 3 | Account | M | Feature | DONE | PgAccountRepository + migrations | P0
STORY-AC-04 | API: POST /accounts | Epic 3 | Account | M | Feature | DONE | Handler account opening | P0
STORY-AC-05 | API: GET /accounts/{id} + list | Epic 3 | Account | M | Feature | DONE | Handlers list + detail | P0
STORY-AC-06 | API: POST /accounts/{id}/movements | Epic 3 | Account | M | Feature | DONE | Handler deposit/withdraw | P0
STORY-AC-07 | Feature: Balance + available_balance | Epic 3 | Account | M | Feature | DONE | Balance tracking avec freeze integration | P0
STORY-AC-08 | Feature: Account statements + reconciliation | Epic 3 | Account | L | Feature | PARTIEL | GET /statement existe, export CSV/PDF non implemente | P2
EPIC 4 - CREDIT (BC3)
STORY-CR-01 | Domain: Loan aggregate + classification | Epic 4 | Credit | L | Feature | DONE | Loan + Classification IFRS9 + RepaymentSchedule (1014 lines) | P0
STORY-CR-02 | Application: LoanService + ports | Epic 4 | Credit | M | Feature | DONE | Service complet (661 lines) | P0
STORY-CR-03 | Infra: Loan + Schedule tables | Epic 4 | Credit | M | Feature | DONE | PgCreditRepository + migrations loans/schedules/classifications | P0
STORY-CR-04 | API: POST /loans | Epic 4 | Credit | M | Feature | DONE | Handler loan creation | P0
STORY-CR-05 | API: GET /loans portfolio view | Epic 4 | Credit | M | Feature | DONE | Handler list + filtres | P0
STORY-CR-06 | Feature: Automatic asset classification | Epic 4 | Credit | M | Feature | DONE | Classification automatique par days_past_due | P0
STORY-CR-07 | Feature: Loan provisioning regulatory | Epic 4 | Credit | M | Feature | DONE | Provisioning rates par asset class | P0
STORY-CR-08 | Feature: Repayment scheduling + amortization | Epic 4 | Credit | M | Feature | A FAIRE | Scheduled job Tokio pour batch quotidien non implemente | P1
EPIC 5 - AML (BC4)
STORY-AML-01 | Domain: Transaction + Alert aggregate | Epic 5 | AML | L | Feature | DONE | Transaction + Alert + Investigation + SuspicionReport + AssetFreeze (1204 lines) | P0
STORY-AML-02 | Application: TransactionMonitoringService | Epic 5 | AML | M | Feature | DONE | Service complet + scenarios (1098 lines) | P0
STORY-AML-03 | Infra: Transaction + Alert tables | Epic 5 | AML | M | Feature | DONE | PgAmlRepository + 7 tables append-only (731 lines) | P0
STORY-AML-04 | API: POST /transactions | Epic 5 | AML | M | Feature | DONE | Handlers complets (578 lines) | P0
STORY-AML-05 | Feature: AML scenarios detection | Epic 5 | AML | M | Feature | DONE | Scenarios complexes implementes | P0
STORY-AML-06 | Feature: Suspicious activity investigation | Epic 5 | AML | M | Feature | DONE | Investigation workflow + notes | P0
STORY-AML-07 | Feature: DOS report + CTAF | Epic 5 | AML | M | Feature | DONE | SuspicionReport generation | P0
STORY-AML-08 | Feature: Asset freeze + workflow | Epic 5 | AML | M | Feature | A FAIRE | AssetFreeze domain OK, integration Account available_balance a finaliser | P1
EPIC 6 - SANCTIONS (BC5)
STORY-SAN-01 | Domain: SanctionEntry + ScreeningResult | Epic 6 | Sanctions | L | Feature | DONE | SanctionList + Entry + ScreeningResult (667 lines) | P0
STORY-SAN-02 | Application: SanctionsScreeningService | Epic 6 | Sanctions | M | Feature | DONE | Service + fuzzy matching (551 lines) | P0
STORY-SAN-03 | Infra: Sanctions list sync | Epic 6 | Sanctions | M | Feature | DONE | PgSanctionsRepository + tables | P0
STORY-SAN-04 | API: GET /sanctions/check | Epic 6 | Sanctions | M | Feature | DONE | Handler screening | P0
STORY-SAN-05 | Feature: Fuzzy matching | Epic 6 | Sanctions | M | Feature | DONE | MatchingStrategy + fuzzy_matcher | P0
STORY-SAN-06 | Feature: Screening on payment (INV-14) | Epic 6 | Sanctions | M | Feature | DONE | Integration Payment context | P0
STORY-SAN-07 | Feature: List update automation | Epic 6 | Sanctions | M | Feature | DONE | List management endpoints | P0
STORY-SAN-08 | Feature: Sanctions dashboard | Epic 6 | Sanctions | M | Feature | A FAIRE | Dashboard endpoint existe, frontend UI manquant | P2
EPIC 7 - PRUDENTIAL (BC6)
STORY-PRU-01 | Domain: PrudentialRatio aggregate | Epic 7 | Prudential | L | Feature | DONE | RatioCalculation + SolvencyCheck + Tier1Capital + ConcentrationLimit (1018 lines) | P0
STORY-PRU-02 | Application: RatioCalculationService | Epic 7 | Prudential | M | Feature | DONE | Service complet (503 lines) | P0
STORY-PRU-03 | Infra: Ratio tables + snapshots | Epic 7 | Prudential | M | Feature | DONE | PgPrudentialRepository + migrations | P0
STORY-PRU-04 | API: GET /prudential/ratios | Epic 7 | Prudential | M | Feature | DONE | Handlers ratios + alerts | P0
STORY-PRU-05 | Feature: Solvency ratio (min 10%) | Epic 7 | Prudential | M | Feature | DONE | Solvency check implemente | P0
STORY-PRU-06 | Feature: Tier 1 ratio (min 7%) | Epic 7 | Prudential | M | Feature | DONE | Tier1Capital check | P0
STORY-PRU-07 | Feature: C/D ratio (max 120%) | Epic 7 | Prudential | M | Feature | DONE | CreditDepositRatio check | P0
STORY-PRU-08 | Feature: Concentration risk (max 25%) | Epic 7 | Prudential | M | Feature | A FAIRE | ConcentrationLimit domain OK, scheduled monitoring non implemente | P1
EPIC 8 - ACCOUNTING (BC7)
STORY-ACC-01 | Domain: JournalEntry + Ledger | Epic 8 | Accounting | L | Feature | DONE | JournalEntry + LedgerAccount + TrialBalance + PeriodClose + ECL (901 lines) | P0
STORY-ACC-02 | Application: AccountingService | Epic 8 | Accounting | M | Feature | DONE | Service complet (748 lines) | P0
STORY-ACC-03 | Infra: Accounting tables (NCT) | Epic 8 | Accounting | M | Feature | DONE | PgAccountingRepository + migrations | P0
STORY-ACC-04 | API: POST /accounting/entries | Epic 8 | Accounting | M | Feature | DONE | Handler manual posting | P0
STORY-ACC-05 | Feature: Automatic entries | Epic 8 | Accounting | M | Feature | DONE | Entry creation/reversal | P0
STORY-ACC-06 | Feature: General ledger + trial balance | Epic 8 | Accounting | M | Feature | DONE | Ledger + trial balance endpoints | P0
STORY-ACC-07 | Feature: Period closing + reconciliation | Epic 8 | Accounting | M | Feature | DONE | PeriodClose implemente | P0
STORY-ACC-08 | Feature: IFRS 9 ECL staging | Epic 8 | Accounting | M | Feature | A FAIRE | ECL_Staging domain OK, calculs PD/LGD a connecter au Credit BC | P1
EPIC 9 - GOVERNANCE (BC11)
STORY-GOV-01 | Domain: AuditTrail aggregate | Epic 9 | Governance | L | Feature | DONE | AuditLog + RoleBasedAccess + PolicyManagement + BctCompliance (1006 lines) | P0
STORY-GOV-02 | Application: AuditService | Epic 9 | Governance | M | Feature | DONE | Service complet (804 lines) | P0
STORY-GOV-03 | Infra: Audit tables (append-only) | Epic 9 | Governance | M | Feature | DONE | PgGovernanceRepository + migrations (617 lines) | P0
STORY-GOV-04 | API: GET /audit | Epic 9 | Governance | M | Feature | DONE | Handlers audit + BCT audit (441 lines) | P0
STORY-GOV-05 | Feature: Audit trail + integrity checks | Epic 9 | Governance | M | Feature | DONE | Append-only persistence | P0
STORY-GOV-06 | Feature: Compliance reports (3 lines defense) | Epic 9 | Governance | M | Feature | DONE | BCT compliance reporting | P0
STORY-GOV-07 | Feature: Committee governance | Epic 9 | Governance | M | Feature | A FAIRE | PolicyManagement domain OK, workflow comite non implemente | P2
STORY-GOV-08 | Feature: Control checks + sign-off | Epic 9 | Governance | M | Feature | A FAIRE | Non implemente - workflow de validation des controles | P2
STORY-AUD-01 | API: Audit trail portal BCT | Epic 9 | Governance | L | Feature | DONE | BCT audit handlers implementes | P0
STORY-AUD-02 | Feature: Audit dashboard supervisors | Epic 9 | Governance | M | Feature | DONE | Frontend AuditDashboard + AuditLogPage | P0
EPIC 10 - REPORTING (BC8)
STORY-REP-01 | Domain: RegulatoryReport aggregate | Epic 10 | Reporting | L | Feature | DONE | Report + Template + FormSubmission + IfrsSubmission (664 lines) | P0
STORY-REP-02 | Application: ReportingService | Epic 10 | Reporting | M | Feature | DONE | Service complet (301 lines) | P0
STORY-REP-03 | Infra: Report tables + generation | Epic 10 | Reporting | M | Feature | DONE | PgReportingRepository + migrations | P0
STORY-REP-04 | API: GET /reporting/forms | Epic 10 | Reporting | M | Feature | DONE | Handlers reports + templates | P0
STORY-REP-05 | Feature: BCT forms generation | Epic 10 | Reporting | M | Feature | DONE | Generate + validate + submit | P0
STORY-REP-06 | Feature: Report submission + acknowledgment | Epic 10 | Reporting | M | Feature | DONE | Acknowledge endpoint | P0
STORY-REP-07 | Feature: Audit logs for reporting | Epic 10 | Reporting | M | Feature | DONE | Audit integration | P0
STORY-REP-08 | Feature: IFRS 9 reporting prep | Epic 10 | Reporting | M | Feature | A FAIRE | IFRS9 handler existe, connexion donnees ECL Accounting incomplete | P1
EPIC 11 - PAYMENT (BC9)
STORY-PAY-01 | Domain: PaymentOrder aggregate | Epic 11 | Payment | L | Feature | DONE | Payment + Screen + ClearingRun + Settlement (1135 lines) | P0
STORY-PAY-02 | Application: PaymentService | Epic 11 | Payment | M | Feature | DONE | Service complet (747 lines) | P0
STORY-PAY-03 | Infra: Payment tables | Epic 11 | Payment | M | Feature | DONE | PgPaymentRepository + migrations | P0
STORY-PAY-04 | API: POST /payments/transfers | Epic 11 | Payment | M | Feature | DONE | Handlers payment lifecycle | P0
STORY-PAY-05 | Feature: SWIFT integration (ISO 20022) | Epic 11 | Payment | M | Feature | DONE | Stub ISO 20022 present | P0
STORY-PAY-06 | Feature: Clearing & compensation | Epic 11 | Payment | M | Feature | DONE | ClearingRun implemente | P0
STORY-PAY-07 | Feature: Payment status tracking | Epic 11 | Payment | M | Feature | DONE | Status endpoint | P0
STORY-PAY-08 | Feature: Sanctions screening on payment | Epic 11 | Payment | M | Feature | A FAIRE | PaymentScreen domain OK, integration real-time Sanctions BC incomplete | P1
EPIC 12 - FOREIGN EXCHANGE (BC10)
STORY-FX-01 | Domain: FxOperation aggregate | Epic 12 | FX | L | Feature | DONE | FxOperation + ExchangeRate + FxPosition + DailyLimit (851 lines) | P0
STORY-FX-02 | Application: FxService (Loi 76-18) | Epic 12 | FX | M | Feature | DONE | Service complet (514 lines) | P0
STORY-FX-03 | Infra: FX tables | Epic 12 | FX | M | Feature | DONE | PgFxRepository + migrations | P0
STORY-FX-04 | API: POST /fx/operations | Epic 12 | FX | M | Feature | DONE | Handlers operations + rates | P0
STORY-FX-05 | Feature: Exchange rate management | Epic 12 | FX | M | Feature | DONE | Rate management endpoints | P0
STORY-FX-06 | Feature: FX position monitoring | Epic 12 | FX | M | Feature | DONE | Position tracking | P0
STORY-FX-07 | Feature: Compliance Loi 76-18 | Epic 12 | FX | M | Feature | DONE | Compliance checks | P0
STORY-FX-08 | Feature: Daily limits enforcement | Epic 12 | FX | M | Feature | A FAIRE | DailyLimit domain OK, scheduled enforcement non implemente | P1
FRONTEND UI STORIES
STORY-F-Auth | Authentication & Authorization UI | Frontend | Identity | M | Feature | DONE | LoginForm + RegisterForm + TwoFactorSetup | P0
STORY-F-Customer | Customer Management & KYC Form | Frontend | Customer | L | Feature | DONE | KycWizard 5 etapes complet | P0
STORY-F-Accounts | Account Dashboard & Operations | Frontend | Account | M | Feature | DONE | AccountListPage + Detail + Movements + Transfer | P0
STORY-F-Dashboards | Risk & Prudential Dashboards | Frontend | Prudential | L | Feature | PARTIEL | RiskDashboard OK, dashboards Credit/AML/Payment manquants | P1
STORY-F-Audit | Audit Trail Viewer | Frontend | Governance | M | Feature | PARTIEL | AuditLogPage OK, BCT audit-bct page OK, filtres a enrichir | P2
STORY-F-RTL | RTL Support for Arabic UI | Frontend | i18n | M | Feature | A FAIRE | rtl.css existe mais integration incomplete dans composants | P2
INTERNATIONALISATION (i18n)
STORY-I18N-01 | i18n Framework Setup | i18n | Transversal | M | Tech | DONE | i18n.ts + fr.json + en.json + ar.json | P0
STORY-I18N-02 | Translation Keys - Identity | i18n | Identity | S | Content | DONE | Cles de traduction presentes | P1
STORY-I18N-03 | Translation Keys - Customer | i18n | Customer | S | Content | DONE | Cles de traduction presentes | P1
STORY-I18N-04 | Translation Keys - Account | i18n | Account | S | Content | PARTIEL | Cles partielles, manque messages erreur | P2
STORY-I18N-05 | RTL CSS & Layout Fixes | i18n | Frontend | M | Tech | PARTIEL | rtl.css existe, layout bugs probables | P2
STORY-I18N-06 | Arabic (Tunisian) Review | i18n | Transversal | M | Content | A FAIRE | Review native speaker necessaire | P2
STORY-I18N-07 | Form Validation Messages (3 langues) | i18n | Transversal | M | Content | A FAIRE | Messages validation non traduits | P2
STORY-I18N-08 | Date/Currency Formatting | i18n | Transversal | M | Tech | A FAIRE | TND/EUR/USD formatting non implemente | P1
HORIZONTAL (RETENTION / CONSENT)
STORY-RET-01 | Feature: Data Retention (INV-10) | Horizontal | Customer | M | Feature | DONE | RetentionService implemente | P0
STORY-CONS-01 | Feature: INPDP Consent Management | Horizontal | Customer | M | Feature | DONE | ConsentService + ConsentRepository + handlers | P0
STORY-CONS-02 | Feature: INPDP Rights Management | Horizontal | Customer | M | Feature | PARTIEL | DataRightsService existe, portabilite export a finaliser | P1
COMPLIANCE ISO 27001 / INPDP (BC13)
STORY-COMP-01 | Domain: SmsiControl, RiskEntry | Compliance | BC13 | M | Feature | A FAIRE | Non implemente - entites SMSI manquantes | P1
STORY-COMP-02 | Domain: TokenVault PCI DSS (INV-16) | Compliance | BC13 | L | Feature | A FAIRE | Non implemente - chiffrement tokenisation | P1
STORY-COMP-03 | Application: ComplianceService | Compliance | BC13 | M | Tech | A FAIRE | Non implemente - service compliance central | P1
STORY-COMP-04 | Infra: Tables compliance + migrations | Compliance | BC13 | M | Tech | A FAIRE | Non implemente - schema DB compliance | P1
STORY-COMP-05 | API: Endpoints SMSI ISO 27001 | Compliance | BC13 | M | Feature | A FAIRE | Non implemente - endpoints controles SMSI | P1
STORY-COMP-06 | Domain: Consent aggregate (INV-19) | Compliance | BC13 | L | Feature | PARTIEL | ConsentRecord existe dans Customer, a migrer vers BC13 | P1
STORY-COMP-07 | API: Consent Management + Dashboard | Compliance | BC13 | M | Feature | PARTIEL | Handlers existent dans Customer, dashboard client manquant | P1
STORY-COMP-08 | Feature: DPIA + Notification violations | Compliance | BC13 | M | Feature | A FAIRE | Non implemente - DPIA et notifications breaches | P1
STORY-COMP-09 | Feature: Portabilite + effacement | Compliance | BC13 | M | Feature | PARTIEL | DataRightsService partiel, effacement non implemente | P1
STORY-COMP-10 | Feature: Integration goAML (CTAF) | Compliance | BC13+AML | L | Feature | A FAIRE | Non implemente - format goAML XML | P2
STORY-COMP-11 | Feature: Integration TuniCheque | Compliance | BC13+Payment | M | Feature | A FAIRE | Non implemente - Circ. 2025-03 | P2
STORY-COMP-12 | Feature: e-KYC biometrique | Compliance | BC13+Identity | L | Feature | A FAIRE | Non implemente - Circ. 2025-06 | P2
STORY-COMP-13 | Feature: Travel Rule R.16 (INV-20) | Compliance | BC13+Payment | M | Feature | A FAIRE | Non implemente - donnees originateur/beneficiaire | P2
STORY-COMP-14 | Feature: MFA pour acces CDE (INV-17) | Compliance | BC13+Identity | M | Feature | DONE | 2FA TOTP implemente couvre ce besoin | P0
STORY-COMP-15 | Feature: Open Banking APIs (PSD3) | Compliance | BC13 | L | Feature | A FAIRE | Non implemente - API open banking | P3

## Roadmap TODO
# | Story ID | Titre | Sprint | BC | Taille | Effort (h) | Dependances | Categorie gap
SPRINT A: FINALISER LES PARTIELS BACKEND (P0/P1)
1 | STORY-T04 | Completer BDD step definitions (12 BC) | A | All | L | 8 | Aucune | Tests
2 | STORY-T08 | Implementer endpoint /metrics Prometheus dans Rust | A | Infra | M | 3 | Aucune | Monitoring
3 | STORY-ID-10 | Session cleanup expired (cron job Tokio) | A | Identity | S | 2 | Aucune | Securite
4 | STORY-ID-08 | Audit trail changement de roles | A | Identity | S | 2 | Aucune | Securite
5 | STORY-C08 | Risk scoring versioning (v1/v2 regles) | A | Customer | M | 3 | Aucune | Metier
SPRINT B: FEATURES BACKEND MANQUANTES (P1)
6 | STORY-CR-08 | Batch job classification quotidien (Tokio) | B | Credit | M | 4 | STORY-CR-06 | Metier
7 | STORY-AML-08 | Integration AssetFreeze <> Account balance | B | AML+Account | M | 4 | STORY-AML-01 | Metier
8 | STORY-ACC-08 | ECL staging connexion Credit BC (PD/LGD) | B | Accounting | L | 5 | STORY-CR-06 | Reglementaire
9 | STORY-PRU-08 | Concentration monitoring schedule | B | Prudential | M | 3 | Aucune | Reglementaire
10 | STORY-PAY-08 | Sanctions screening real-time sur paiements | B | Payment+Sanctions | M | 4 | STORY-SAN-06 | Reglementaire
11 | STORY-REP-08 | IFRS 9 reporting data pipeline ECL | B | Reporting | M | 4 | #8 (ACC-08) | Reglementaire
12 | STORY-FX-08 | Daily limits enforcement scheduled | B | FX | M | 3 | Aucune | Reglementaire
13 | STORY-AC-08 | Export releves CSV + PDF | B | Account | M | 4 | Aucune | UX
14 | STORY-CONS-02 | Portabilite donnees export complet | B | Customer | M | 3 | Aucune | RGPD/INPDP
SPRINT C: COMPLIANCE BC13 - ISO 27001 / INPDP (P1)
15 | STORY-COMP-01 | Entites SMSI (SmsiControl, RiskEntry) | C | BC13 | M | 4 | Aucune | ISO 27001
16 | STORY-COMP-02 | TokenVault chiffrement PCI DSS | C | BC13 | L | 6 | Aucune | PCI DSS
17 | STORY-COMP-03 | ComplianceService + ports | C | BC13 | M | 4 | #15 #16 | ISO 27001
18 | STORY-COMP-04 | Tables compliance + migrations SQL | C | BC13 | M | 3 | #17 | ISO 27001
19 | STORY-COMP-05 | Endpoints SMSI ISO 27001 | C | BC13 | M | 4 | #18 | ISO 27001
20 | STORY-COMP-06 | Migrer Consent vers BC13 | C | BC13 | L | 5 | #17 | INPDP
21 | STORY-COMP-07 | Dashboard client consentement | C | BC13 | M | 4 | #20 | INPDP
22 | STORY-COMP-08 | DPIA + Notification violations | C | BC13 | M | 4 | #17 | INPDP
23 | STORY-COMP-09 | Portabilite + droit a effacement | C | BC13 | M | 4 | #20 | INPDP
SPRINT D: INTEGRATIONS EXTERNES (P2)
24 | STORY-COMP-10 | Integration goAML format XML (CTAF) | D | BC13+AML | L | 6 | #19, AML-07 | Reglementaire
25 | STORY-COMP-11 | Integration TuniCheque (Circ. 2025-03) | D | BC13+Payment | M | 4 | #19 | Reglementaire
26 | STORY-COMP-13 | Travel Rule R.16 donnees paiement | D | BC13+Payment | M | 4 | PAY-04 | Reglementaire
27 | STORY-COMP-12 | e-KYC biometrique (Circ. 2025-06) | D | BC13+Identity | L | 8 | ID-01 | Innovation
SPRINT E: FRONTEND - PAGES MANQUANTES (P1/P2)
28 | STORY-F-Dashboards | Dashboards Credit/AML/Payment | E | Frontend | L | 8 | API backend OK | UX
29 | STORY-SAN-08 | Sanctions screening dashboard UI | E | Frontend | M | 4 | API backend OK | UX
30 | STORY-F-RTL | RTL Arabic integration complete | E | Frontend | M | 4 | I18N-05 | i18n
31 | STORY-I18N-08 | TND/EUR/USD currency formatting | E | Frontend | M | 3 | I18N-01 | i18n
32 | STORY-I18N-04 | Translation keys Account (erreurs) | E | Frontend | S | 2 | I18N-01 | i18n
33 | STORY-I18N-05 | RTL CSS fixes layout | E | Frontend | M | 3 | Aucune | i18n
34 | STORY-I18N-07 | Form validation messages 3 langues | E | Frontend | M | 3 | I18N-01 | i18n
35 | STORY-I18N-06 | Arabic review par native speaker | E | Frontend | M | 3 | I18N-05 | i18n
SPRINT F: GOVERNANCE + NICE-TO-HAVE (P2/P3)
36 | STORY-GOV-07 | Workflow comite governance | F | Governance | M | 4 | GOV-01 | Gouvernance
37 | STORY-GOV-08 | Control checks + sign-off | F | Governance | M | 4 | GOV-07 | Gouvernance
38 | STORY-COMP-15 | Open Banking APIs (PSD3-ready) | F | BC13 | L | 8 | Tous les BC core | Innovation
39 | STORY-F-Audit | Enrichir filtres audit viewer | F | Frontend | S | 2 | Aucune | UX
40 | - | CHANGELOG.md + docs/METRICS.md | F | Docs | S | 2 | Aucune | Documentation
TOTAL | [5 empty] | 162 | ~20 jours de travail

## Gap par BC
Bounded Context | Domain | Application | Infrastructure | Database | Frontend | Tests BDD | Score global | Gap principal
Identity (BC12) | 90% | 100% | 100% | 100% | 100% | 70% | 93.3333 | Session cleanup, audit roles
Customer (BC1) | 100% | 100% | 100% | 100% | 95% | 70% | 94.1667 | Risk scoring versioning
Account (BC2) | 100% | 100% | 100% | 100% | 95% | 70% | 94.1667 | Export CSV/PDF releves
Credit (BC3) | 100% | 100% | 100% | 100% | 10% | 70% | 80 | Batch job + frontend
AML (BC4) | 100% | 100% | 100% | 100% | 10% | 70% | 80 | Freeze<>balance + frontend
Sanctions (BC5) | 100% | 100% | 100% | 100% | 10% | 70% | 80 | Dashboard UI
Prudential (BC6) | 100% | 100% | 100% | 100% | 60% | 70% | 88.3333 | Concentration monitoring
Accounting (BC7) | 100% | 100% | 100% | 100% | 10% | 70% | 80 | ECL staging connexion
Reporting (BC8) | 100% | 100% | 100% | 100% | 10% | 70% | 80 | IFRS9 data pipeline
Payment (BC9) | 100% | 100% | 100% | 100% | 10% | 70% | 80 | Sanctions realtime + frontend
ForeignExchange (BC10) | 100% | 100% | 100% | 100% | 10% | 70% | 80 | Daily limits + frontend
Governance (BC11) | 100% | 100% | 100% | 100% | 80% | 70% | 91.6667 | Comite + sign-off
Compliance (BC13) | 15% | 10% | 10% | 0% | 0% | 0% | 5.8333 | Contexte entier a creer

## Stories Additionnelles
# | Story ID | Titre | BC | Taille | Effort (h) | Priorite | Justification | Sprint suggere
MODULE NOTIFICATIONS & ALERTES
1 | STORY-NOT-01 | Domain: Notification aggregate (Email/SMS/Push) | Transversal | L | 6 | P1 | Tout core banking doit notifier les clients. Aucun module notification dans BANKO. | G
2 | STORY-NOT-02 | Application: NotificationService + templates | Transversal | M | 4 | P1 | Service d'orchestration avec templates multilingues (FR/EN/AR) | G
3 | STORY-NOT-03 | Infra: Provider Email (SMTP/SendGrid) + SMS gateway | Transversal | M | 4 | P1 | Adaptateurs pour envoi reel. SMS critique pour Tunisie (2FA, alertes) | G
4 | STORY-NOT-04 | Infra: Tables + queue async (Tokio tasks) | Transversal | M | 3 | P1 | Persistance + retry + queue asynchrone pour fiabilite | G
5 | STORY-NOT-05 | Feature: Preferences client (opt-in/opt-out canaux) | Transversal | M | 3 | P2 | INPDP/RGPD: le client doit choisir ses canaux de notification | G
6 | STORY-NOT-06 | Feature: Alertes transactionnelles temps reel | Transversal | M | 3 | P1 | Alertes debit/credit, seuil depasse, tentative login suspecte | G
MODULE CATALOGUE PRODUITS BANCAIRES
7 | STORY-PROD-01 | Domain: Product aggregate (taux, frais, conditions) | Account+Credit | L | 6 | P1 | Un CBS doit parametrer ses produits (compte courant, epargne, DAT, credit conso, immo...) | H
8 | STORY-PROD-02 | Application: ProductService + pricing engine | Account+Credit | M | 4 | P1 | Moteur de tarification: frais tenue compte, commissions, taux | H
9 | STORY-PROD-03 | Feature: Grille tarifaire configurable | Account+Credit | M | 4 | P1 | Admin configure les frais par produit, segment client, devise | H
10 | STORY-PROD-04 | Feature: Calcul interets automatique (DAT, epargne) | Account | M | 4 | P1 | Interets credites periodiquement (daily accrual, monthly posting) | H
MODULE GESTION CARTES BANCAIRES
11 | STORY-CARD-01 | Domain: Card aggregate (emission, activation, blocage) | Payment | L | 6 | P1 | Gestion cartes debit/credit indispensable. BANKO n'a aucun module carte. | I
12 | STORY-CARD-02 | Application: CardService + lifecycle management | Payment | M | 4 | P1 | Emission, activation, renouvellement, opposition, blocage/deblocage | I
13 | STORY-CARD-03 | Infra: Tables cards + card_transactions | Payment | M | 3 | P1 | Schema DB pour cartes et autorisations | I
14 | STORY-CARD-04 | API: Endpoints gestion cartes | Payment | M | 4 | P1 | POST/GET/PUT /cards, /cards/{id}/block, /cards/{id}/activate | I
15 | STORY-CARD-05 | Feature: Plafonds et limites par carte | Payment | M | 3 | P1 | Limites retrait DAB, paiement commerce, en ligne. Modifiables par client. | I
16 | STORY-CARD-06 | Feature: Tokenisation carte (PCI DSS) | Payment+Compliance | L | 6 | P1 | Stockage securise PAN via tokenisation. Lie a STORY-COMP-02. | I
MODULE VIREMENTS RECURRENTS & PRELEVEMENTS
17 | STORY-RECUR-01 | Feature: Virements permanents (standing orders) | Payment | M | 4 | P1 | Virements automatiques periodiques (loyer, epargne auto). Absent de BANKO. | H
18 | STORY-RECUR-02 | Feature: Prelevements (direct debit mandats) | Payment | M | 4 | P1 | Gestion mandats de prelevement SEPA/domestique. Essentiel pour factures. | H
19 | STORY-RECUR-03 | Feature: Scheduler paiements recurrents (Tokio cron) | Payment | M | 4 | P1 | Job batch pour execution des ordres permanents a date definie | H
MODULE MULTI-DEVISE COMPTES
20 | STORY-MCUR-01 | Feature: Comptes multi-devises (TND, EUR, USD) | Account+FX | L | 6 | P1 | Clients doivent pouvoir detenir des sous-comptes en devise. Lie au FX. | I
21 | STORY-MCUR-02 | Feature: Conversion automatique inter-comptes | Account+FX | M | 4 | P2 | Virement entre sous-comptes avec taux FX du jour applique | I
MODULE FRAIS & COMMISSIONS
22 | STORY-FEE-01 | Domain: Fee aggregate (type, montant, conditions) | Accounting | M | 4 | P1 | Moteur de frais: tenue de compte, virement, retrait DAB, chequier... | H
23 | STORY-FEE-02 | Feature: Calcul et prelevement automatique des frais | Accounting | M | 4 | P1 | Frais debites automatiquement avec ecriture comptable associee | H
24 | STORY-FEE-03 | Feature: Grille frais par segment client | Accounting | M | 3 | P2 | Particulier vs. Entreprise vs. Premium: frais differencies | H
MODULE GESTION CHEQUES
25 | STORY-CHQ-01 | Domain: Cheque aggregate (emission, encaissement, rejet) | Payment | M | 4 | P1 | Cheques toujours utilises en Tunisie. Gestion emission, compensation, rejet. | I
26 | STORY-CHQ-02 | Feature: Opposition cheque + interdit bancaire | Payment | M | 3 | P1 | Lien avec TuniCheque (STORY-COMP-11). Declaration interdits bancaires. | I
27 | STORY-CHQ-03 | Feature: Compensation cheques (chambre compensation BCT) | Payment | M | 4 | P2 | Integration systeme de compensation BCT pour cheques | I
MODULE EVENT BUS & INTEGRATION INTER-BC
28 | STORY-EVT-01 | Feature: Event bus interne (domain events) | Transversal | L | 6 | P1 | Les 12 BC communiquent par appels directs. Un event bus decouple les interactions. | G
29 | STORY-EVT-02 | Feature: Event store + replay | Transversal | L | 6 | P2 | Audit trail renforce: tous les events persistes, rejouables pour debug/migration | J
30 | STORY-EVT-03 | Feature: Saga pattern pour transactions cross-BC | Transversal | L | 8 | P2 | Compensation automatique si un BC echoue (ex: paiement -> AML -> comptabilite) | J
MODULE SECURITE AVANCEE & ANTI-FRAUDE
31 | STORY-SEC-01 | Feature: Rate limiting API (Actix middleware) | Identity | M | 3 | P1 | Protection brute force. Mentionne dans stories mais non implemente. | G
32 | STORY-SEC-02 | Feature: Detection fraude temps reel (rules engine) | AML+Payment | L | 8 | P2 | Au-dela de l'AML: detection comportement anormal (geo, montant, heure) | J
33 | STORY-SEC-03 | Feature: IP whitelisting + geo-blocking | Identity | M | 3 | P2 | Blocage connexions depuis pays sanctionnes ou IP suspectes | J
34 | STORY-SEC-04 | Feature: Audit cryptographique (hash chain) | Governance | M | 4 | P2 | Chaque audit log lie au precedent par hash = inalterable (blockchain-like) | J
MODULE BUSINESS INTELLIGENCE & ANALYTICS
35 | STORY-BI-01 | Feature: Dashboard operationnel temps reel | Reporting | L | 6 | P2 | Vue consolidee: nb comptes, volume tx, encours credit, liquidite | J
36 | STORY-BI-02 | Feature: Export donnees pour BI externe (Metabase/Grafana) | Reporting | M | 4 | P2 | Vues SQL read-only ou API GraphQL pour outils BI tiers | J
37 | STORY-BI-03 | Feature: Alertes business automatisees | Reporting | M | 3 | P2 | Alertes quand ratio prudentiel approche seuil, encours credits trop concentre | J
MODULE MOBILE BANKING
38 | STORY-MOB-01 | Feature: API mobile-optimisee (REST + compression) | Transversal | M | 4 | P2 | Endpoints optimises mobile: pagination, champs reduits, compression gzip | K
39 | STORY-MOB-02 | Feature: Push notifications (Firebase/APNs) | Transversal | M | 4 | P2 | Integration push pour alertes temps reel sur mobile | K
40 | STORY-MOB-03 | Feature: Authentification biometrique mobile | Identity | M | 4 | P2 | Login par empreinte/Face ID via WebAuthn/FIDO2 | K
MODULE BACKUP & DISASTER RECOVERY
41 | STORY-DR-01 | Feature: Backup automatise PostgreSQL (pg_dump + S3) | Infra | M | 4 | P1 | Backup quotidien automatise vers MinIO/S3. Aucun script de backup dans BANKO. | G
42 | STORY-DR-02 | Feature: Point-in-time recovery (PITR) | Infra | M | 4 | P1 | WAL archiving pour restauration a un instant precis. Critique pour banque. | G
43 | STORY-DR-03 | Feature: Disaster recovery plan + runbook | Infra | M | 3 | P1 | Documentation + scripts de bascule. Exigence regulateur. | G
MODULE END-OF-DAY (EOD) PROCESSING
44 | STORY-EOD-01 | Feature: Job EOD orchestrateur | Transversal | L | 6 | P1 | Batch de fin de journee: calcul interets, frais, classification, ratios. Absent de BANKO. | H
45 | STORY-EOD-02 | Feature: Calcul interets quotidien (accrual) | Account+Credit | M | 4 | P1 | Interets courus calcules chaque jour, comptabilises mensuellement | H
46 | STORY-EOD-03 | Feature: Reconciliation automatique EOD | Accounting | M | 4 | P1 | Verification balance comptable = somme soldes comptes. Detecte anomalies. | H
TOTAL |  |  |  |  | 199 | ~24 jours